## Slide 2: Key Credit Story Benefits
Many of the attributes that make the modular product attractive to developers also enhance the credit story for lenders
Reduce Construction Period by 30-50%
Single party responsible for major portion of the build minimizing reliance on/ confusion related to sub contractors
Cost certainty on a major portion of the project budget
Reduced exposure to schedule delays from safety issues, weather, theft or fire
Higher quality asset – acoustic performance and repeat activities performed in a controlled environment
Faster lease up means less market risk

## Slide 3: Common Concerns & Mitigants
Common Concern | Mitigant
Large Deposit | Initial draw covers pre-identified, project-specific set of materials, partially covered by equity Used to procure finish goods as well as raw materials (cabinets, flooring, plumbing and electrical fixtures, etc.)
Funding Materials Not at Site | Raw goods stored in climate controlled factory, not outside in the elements Lender can inspect and inventory at any time in the factory Finished goods have trackable serial number Lender can perfect a security interest in the project assets
Accelerated Drawdown | Use of escrow account with releases based on verified performance and completion Compressed construction timeline means sooner lease up
Security and Collateral | First position security interest in all project assets Conditional and unconditional lien releases on draws from escrow
Inspection Process | Black and white pay points certified by multiple 3rd party inspectors including building, client acceptance and bank designated inspectors
Insurance Continuity | Full coverage from procurement to transportation to installation At our facility – physical damage property insurance, general liability and workers comp Onsite – pre-install property coverage, builders risk, general liability for project completed products and workers comp

## Slide 4: Payment Schedule & Collateral Flow
Months |  |  |  |  |  |  |  |  |  | 
1 -6 |  | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Typical Rise Modular Payment Schedule (% of Total Invoice) |  |  |  |  |  |  |  |  |  | 
2% |  | 3% | - | 40% | 20% | 20% | 10% | 5% |  | 
Cumulative |  | 5% |  | 45% | 65% | 85% | 95% | 100% |  | 
Collateral (Cumulative %’s) |  |  |  |  |  |  |  |  |  | 
Raw Materials In Transit or @ Facility |  | - | - | 100% | 75% | 25% |  |  |  | 
WIP Modules @ Facility |  | - | - |  | 25% | 50% | 25% |  |  | 
Completed Modules | @ Third Party Storage | - | - |  |  | 25% | 75% |  |  | 
 | @ Construction Site | - | - |  |  |  |  | 100% |  | 
Total |  |  |  | 100% | 100% | 100% | 100% | 100% |  | 
Schematic Design, City Approvals And Design and Development Documents | Construction Documents | Permits
Sitework & Foundation
Finish
Set
Offsite Factory Build

## Slide 5: Closing Points
Rise Modular is forming “strategic partnerships” with local banks to provide project financing for our clients
No need to reinvent the wheel – it’s being done on the coasts
Innovation from hotel brands will help guide the way